EEZO Post-Quantum Cryptography Blockchain

Comprehensive Architecture, Plan & Audit Report

Prepared for: EEZO Blockchain Project + OpenAI Partnership
Prepared by: Technical Audit Team
Date: January 15, 2026
Status: Confidential - Development Phase Review

Executive Summary

This audit evaluates the EEZO blockchain project's architecture, design, implementation status, and strategic bottlenecks across parallel DevNet/TestNet/MainNet development pipelines. The assessment covers cryptographic infrastructure (T70–T81), consensus mechanisms (HotStuff BFT), networking (KEMTLS post-quantum handshake), and identifies critical gaps preventing production readiness.

Key Findings

Strengths:

- Multi-suite cryptographic governance framework (T79–T80) provides foundational agility for PQ algorithm rotation

- KEMTLS post-quantum handshake implementation (T24–T27) enables secure peer-to-peer connections

- Comprehensive test-driven development with per-task validation gates

- Algorithm-agnostic consensus verifier design maintains future flexibility

Critical Gaps:

- Synchronous Bottleneck — Step-once polling loop blocks TPS scalability and latency targets

- Persistence Gap — RAM-only state violates consensus safety invariants; no durable consensus logs

- Protocol Serialization Gap — Suite IDs not carried on wire; suite rotation fragile and uncoordinated

- Network Runtime Observability — Missing metrics for consensus message rates, queue backpressure, and async overhead

- Load Testing Absence — No scriptable harness to measure node throughput, latency under realistic PQC verification loads

Parallel Deployment Risk:
Developing DevNet/TestNet/MainNet in parallel without foundational persistence or observability creates validation blindness—bugs discovered late in one environment may require architectural rewrites affecting all three.

Part 1: Project Status & Completed Work

1.1 Completed Cryptographic Infrastructure (T70–T81)

Task Sequence Overview

| Task | Title | Status | Outcome |
| --- | --- | --- | --- |
| T70 | Consensus Key Registry & Governance | ✓ Complete | Multi-validator key lookup via traits; governance integration ready |
| T71–T75 | (Prior crypto foundation work) | ✓ | HKDF session keys, AEAD encryption, algorithm-agnostic design |
| T76 | Consensus Signature Verification Trait | ✓ | ConsensusSigVerifier trait, algorithm-agnostic, test SHA3 backend |
| T77 | Multi-Suite Traits & Governance Bridge | ✓ | GovernedValidatorKeyRegistry connects governance to validation |
| T78 | Metrics & Debug Logging for Consensus Sig | ✓ | Per-validator, per-kind metrics; confidential logging (no key/sig data) |
| T79 | Multi-Suite Consensus Key Governance | ✓ | ConsensusSigSuiteId opaque type; SuiteAwareValidatorKeyProvider; per-suite dispatch ready |
| T80 | Integrate MultiSuiteCryptoVerifier | ✓ | Single-backend verifier now delegates to multi-suite; HotStuff driver unified |
| T81 | Carry SuiteId on Wire & Records | ✓ Local Tests | ConsensusSigSuiteId propagated to Vote, Proposal, QC structures; serialization ready |

What These Tasks Achieved

- Algorithm Agnosticism — ConsensusSigVerifier trait does not hardcode crypto algorithms; suite IDs allow future PQ plugging (ML-DSA, SPHINCS+, SLH-DSA, etc.)

- Multi-Suite Governance — Validators can use different signature suites; governance returns suite ID + public key bytes per validator

- Per-Suite Verification Dispatch — MultiSuiteCryptoVerifier looks up the appropriate backend (SHA3 test suite today) and verifies accordingly

- Metrics & Observability — Vote/proposal verification success/failure counts, missing-key detection, latency hooks in place

- Wire Format Readiness (T81) — Suite IDs now part of consensus message structures, but not yet enforced on actual network transport

Current Bottleneck: Suite ID Enforcement & Upgrade Path

- Issue: SuiteIds are in data structures but not yet validated at node startup (T82 was proposed for startup-time checks)

- Risk: Unknown suite ID in a received vote/proposal defaults to generic VerificationErrorOther; no per-suite version negotiation

- Impact: Hybrid transitions (rolling out new PQ suites while running old ones) lack explicit coordination or error reporting

1.2 Consensus & Network Layer (HotStuff + KEMTLS)

HotStuff BFT with Pacemaker

- Status: Implemented and tested (per T0 conversation logs)

- Current: Tick-based synchronous polling loop; commit pruning active

- Missing: Async/await integration; no runtime observability

KEMTLS Post-Quantum Handshake (T24–T27)

- Completed: Stateless cookie mechanism, ClientInit/ServerCookie/ServerAccept flow

- Scope: eezo-net crate, pure-logic cryptographic handshake (no sockets/async yet)

- What Works: Session key derivation, encrypted transport frame format, test coverage for cookie, signature, suite mismatches

- What's Missing: Real socket integration in eezo-node; no async TLS state machine in production path

Connection Orchestration (T28)

- Status: Logical Connection abstraction ready (hands byte frames in/out)

- Scope: Still pure logic; no socket I/O

- Next: Integrate with actual TCP peer-to-peer layer (currently in eezo-node but not tested under load)

Part 2: Strategic Bottlenecks (The Three Necks)

2.1 The Synchronous Neck — Step-Once Polling Loop

Problem:
Current architecture:
┌─────────────────────────────┐
│ eezo-node main loop │
├─────────────────────────────┤
│ while running: │
│ consensus.step_once() │
│ network.step_once() │
│ storage.step_once() │
│ // block until all done │
└─────────────────────────────┘

Why It Bottlenecks TPS & Latency:

- Wasted Wakeups — If consensus has nothing to do, CPU spins waiting for network; network I/O blocks on storage commit

- No Overlapping I/O — Consensus verification waits for network message arrival; network waits for storage ACK before polling again

- PQ Verification Overhead — Verifying ML-DSA or SPHINCS+ signatures (larger signatures than ECC) in a synchronous loop increases worst-case block latency

- Validator Scheduling Fragility — Proposers miss their slot if consensus + disk commit takes longer than block time

Current Measurement:

- No instrumentation yet (T78 metrics are present but not aggregated for end-to-end latency)

- Load harness missing (proposed in T26 context but not built)

Impact on Parallel Deployments:

- DevNet may run fine with 1–10 validators (synchronous overhead masked)

- TestNet with 50+ validators will show degraded block times; MainNet targets unachievable without async

Required Fix:
Move to Tokio async runtime with:

- Async consensus loop (awaiting network messages, storage commits)

- Non-blocking signature verification (GPU-accelerated PQ verification offload)

- Channels and task boundaries (consensus ↔ network ↔ storage decoupled)

Proposed Task: T85 (Design async boundaries; T86+ incremental refactors)

2.2 The Persistence Gap — RAM-Only State

Current State:
Consensus State:
├─ Locked QC (in memory)
├─ Last vote (in memory)
├─ Pacemaker view (in memory)
└─ No persistent log

Ledger State:
├─ Blocks (maybe in memory)
├─ Transactions (maybe in memory)
├─ Balances (memory)
├─ Governance Key Registry (memory)
└─ No on-disk backup

On Node Restart:
├─ All state lost
├─ Cannot rejoin or prove safety history
└─ Audit trail evaporates

Why This Violates Consensus Safety:

- Liveness Assumption Broken — HotStuff assumes nodes remember votes; restart causes equivocation risk if votes aren't durable

- Recovery Undefined — No replay or state rebuilding path; nodes restart from genesis each time (if that works at all)

- Audit Impossibility — No persistent history of decisions; external auditors cannot verify consensus correctness

Impact on Parallel Deployments:

| Environment | Issue | Severity |
| --- | --- | --- |
| DevNet | Crashes lose all state; manual restart required | Medium |
| TestNet | Network instability + state loss = unrecoverable partitions | High |
| MainNet | Unacceptable; violates custody and regulatory requirements | Critical |

Required Fixes (Proposed T83–T84):

- T83: RocksDB-backed persistence layer; trait-based storage abstraction

- T84: Governance key registry persistence; consensus QC/vote logging; auditable ledger state

Estimated Scope:

- 3–5 tasks to make persistence correct and fast

- Must precede TestNet launch

2.3 The Protocol Lag — Suite IDs Not on Wire

Current State:
Wire Format (After T81, not yet deployed):
Vote {
validator_id: u64,
suite_id: ConsensusSigSuiteId, // ← Added in T81 locally
signature: Vec<u8>,
...
}

But in ACTUAL network transmission:

- suite_id may not be serialized yet (depends on codec)

- Or suite_id IS serialized but receiver ignores it

- Or no backward compatibility story if suite_id missing in old messages

Why This Prevents Upgrade Coordination:

- Silent Fallback — If suite_id missing on wire, verifier defaults to SUITETOYSHA3; hides misconfiguration

- No Version Negotiation — When rolling out ML-DSA, no explicit handshake to agree on suite; nodes may quietly verify with wrong algorithm

- Audit Fragility — External bridges/validators cannot reconstruct which suite was used for a vote months after the fact

Example Failure Scenario:
Time T0: Network uses ML-DSA (suite ID 1)
Time T0 + 3 months: Maintainer accidentally deploys with old binary (suite ID 0, SHA3)
Time T0 + 3 months, block N:

- Votes from suite 1 nodes arrive

- Old binary sees no suite_id on wire (backward compat broken)

- Defaults to suite 0, verification fails

- Network halts, consensus dead

Required Fixes (T82, not yet started):

- Ensure suite_id is always on the wire in canonical form

- Reject unknown suite IDs explicitly (not silent fallback)

- Add startup validation that all in-use suite IDs have registered backends

Estimated Scope: 1–2 tasks

Part 3: Architecture Gaps & Blockers

3.1 Network Runtime Observability (Missing from T78–T81)

What Exists (T78 added to CryptoConsensusVerifier):

- Signature verification success/failure counts

- Missing-key detection

- Per-validator, per-message-kind counters

What's Missing:
From T26 context, the original proposal included:

Planned but not yet built:

Part A: Network runtime metrics
├─ Inbound consensus message rates (by kind: vote, proposal, other)
├─ Outbound message rates
├─ Queue occupancy on consensus event channel
├─ spawnblocking usage count and latency
└─ Async node runtime visibility

Part B: Load harness
├─ Single-node load harness (loopback network)
├─ Configurable message injection (votes, proposals)
├─ Prometheus or simple metrics export
└─ Latency histograms (e2e consensus tick)

Why This Matters:

- Without metrics, cannot measure impact of PQ signature verification on throughput

- Cannot diagnose network backpressure under load

- Cannot correlate performance regressions to code changes

Blocking: Tuning for TestNet/MainNet TPS targets

3.2 Load Testing & Performance Validation (Absent)

Missing Tooling:

- No scriptable harness to stress a single node with configurable consensus messages

- No end-to-end latency measurement (proposal submit → committed block)

- No throughput (TPS) baseline for different validator set sizes

- No performance data for ML-DSA, SPHINCS+ signature verification under realistic loads

Current Situation:

- Unit tests pass (per conversation logs)

- No integration tests under network load

- No profile data showing bottleneck (crypto, network, or consensus logic)

Why This Blocks Parallel Deployment:

- DevNet may be "complete" but hitting 1000 TPS is unknown

- TestNet could have undiscovered scaling issues (too late in the pipeline)

- MainNet launch risks hitting performance regression post-deployment

Estimated Effort:

- T26 proposed a straightforward load harness (2–3 tasks)

- Performance profiling (1–2 tasks)

3.3 Governance & Key Rotation Automation (Minimal)

Current State:

- Governance trait returns suite_id + public key bytes per validator

- Suite ID is u16 opaque type (no versioning, no deprecation)

- No explicit key rotation or suite upgrade protocol

What's Missing:

- Mechanism to announce key changes to the network

- Transition period (old + new keys valid simultaneously)

- Explicit "suite A → suite B" protocol

- Validator coordination during rollout

Risk:

- Changing a validator's key in governance may be silent; no network agreement

- Possible acceptance of old votes after key change (if timestamps not checked)

- Difficult audit trail (when did each validator change suites?)

Estimated Scope: 1–2 design tasks + 3–4 implementation tasks (post-launch)

Part 4: Parallel Deployment Strategy Assessment

4.1 Recommended Timeline

Phase 1: Persistence & Protocol Hardening (Weeks 1–4)

Critical Path for TestNet

| Task | Effort | Blocker | Description |
| --- | --- | --- | --- |
| T82 | 1 week | (T81) | Startup validation: all suite_ids have backends; error on unknown suites |
| T83 | 2 weeks | (T82) | RocksDB integration; consensus state durability |
| T84 | 1.5 weeks | (T83) | Governance key registry persistence; audit logging |
| Subtotal | 4.5 weeks | — | Enables TestNet to survive restarts & run audits |

Phase 2: Observability & Load Testing (Weeks 5–8)

Required Before TestNet Public

| Task | Effort | Blocker | Description |
| --- | --- | --- | --- |
| Metrics (T26 proposal) | 1 week | (T78) | Network runtime counters; queue depth; async overhead |
| Load Harness | 1.5 weeks | (T27 transport) | Single-node loopback; configurable message injection; TPS measurement |
| Performance Baseline | 1 week | (Load harness) | Run with toy crypto; measure e2e latency, throughput |
| PQC Perf Profiling | 2 weeks | (Load harness) | Insert ML-DSA verification; measure throughput regression |
| Subtotal | 5.5 weeks | — | Unblocks TestNet TPS validation; reveals bottlenecks |

Phase 3: Async Transition Design & P2P Integration (Weeks 9–14)

Long-lead for MainNet Performance

| Task | Effort | Blocker | Description |
| --- | --- | --- | --- |
| T85 Async Design | 2 weeks | (All Phase 1–2) | Define Tokio task boundaries; consensus ↔ network ↔ storage; channel design |
| T86a Async Consensus | 2 weeks | (T85) | Move consensus step into async; handle message subscriptions |
| T86b Async Network | 2 weeks | (T85) | TCP sockets + KEMTLS handshake in Tokio; backpressure handling |
| T86c Async Storage | 1.5 weeks | (T85) | RocksDB async I/O; buffer consensus writes |
| Subtotal | 7.5 weeks | — | Foundational scalability; ready for MainNet performance targets |

4.2 Risk Matrix: Parallel vs. Sequential Approach

Parallel (Current Plan) — DevNet, TestNet, MainNet in parallel

Timeline Advantage: +8 weeks (all three launch sooner)

Risk/Cost:
├─ Synchronous Neck unknown in DevNet → surprised by in TestNet
├─ Persistence Gap not visible until TestNet crash → MainNet unprepared
├─ Protocol Lag delays upgrade testing → coordination issues at launch
├─ Load Testing absent → MainNet performance unknown until live
├─ Audit review on three codebases in parallel → review fatigue, missed issues
└─ Rollback complexity if Phase 1 issues discovered late

Sequential (Fallback Recommendation) — DevNet → TestNet → MainNet, strict gates

Timeline Penalty: +8 weeks (sequential, but each environment fully validated)

Risk Reduction:
├─ DevNet findings apply to TestNet design (no surprises)
├─ TestNet persistence fully proven before MainNet
├─ Protocol upgrades tested on TestNet before MainNet rollout
├─ Load testing identifies bottlenecks; fixes integrated before MainNet
├─ Single codebase review → higher quality
└─ Clear exit criteria for each gate

Recommended Hybrid (Optimal):

- Finish Phase 1 (Persistence, T82–T84) before DevNet launch — All three can start in parallel after this

- Complete Phase 2 (Observability, T26 + Load harness) before TestNet public — Don't launch TestNet blind

- Start Phase 3 (Async) in TestNet beta — Incremental rollout, measure impact

- MainNet gates: All Phase 1–3 complete, 4+ weeks public TestNet stability, formal audit passed

Part 5: Detailed Gap Analysis

5.1 Cryptographic Stack

| Component | Status | Gaps | Risk |
| --- | --- | --- | --- |
| Algorithm Agnosticism | ✓ Complete | Suite ID enforcement missing (T82) | Medium — silent fallback on wire |
| Multi-Suite Governance | ✓ Complete | No key rotation protocol | High — validator suite changes fragile |
| KEMTLS Handshake | ✓ Logic ready | No socket integration; no async | Medium — peer-to-peer untested under load |
| Session Keys (HKDF) | ✓ Complete | No session reuse/caching | Low — correctness fine, perf improvable |
| AEAD Encryption | ✓ Complete | No authenticated frames for malicious peer detection | Low — not required for correctness |

5.2 Consensus (HotStuff)

| Component | Status | Gaps | Risk |
| --- | --- | --- | --- |
| Core Algorithm | ✓ Complete | Synchronous bottleneck; no backpressure handling | High — TPS ceiling unknown |
| Metrics | ✓ Partial | No e2e latency, throughput histograms | High — cannot diagnose performance issues |
| State Persistence | ✗ Missing | RAM-only; no recovery | Critical — violates safety invariants |
| Network Observability | ✗ Missing | No queue depth, message rate metrics | High — cannot tune network stack |
| Load Harness | ✗ Missing | No scriptable testing; manual load only | High — undiscovered bottlenecks |

5.3 Networking (KEMTLS + P2P)

| Component | Status | Gaps | Risk |
| --- | --- | --- | --- |
| KEMTLS Logic | ✓ Complete | No real TCP socket integration | Medium — assumed to work, untested |
| Connection Abstraction | ✓ Complete | Pure logic, no async I/O | High — synchronous wrapper needed |
| Peer Discovery | ✗ Missing | No bootstrap, seed node, peer routing | Critical — isolated nodes cannot find peers |
| Message Propagation | ✗ Missing | No mempool, block relay, gossip | Critical — consensus cannot advance |
| Backpressure Handling | ✗ Missing | No flow control; unbounded channel growth | High — network stalls under high load |

5.4 Storage & Durability

| Component | Status | Gaps | Risk |
| --- | --- | --- | --- |
| Consensus State Logging | ✗ Missing | No QC, vote, proposal persistence | Critical — consensus safety violated on restart |
| Ledger State | ✗ Missing | No block/transaction durability | Critical — cannot verify chain after restart |
| Governance Registry | ✗ Missing | No persistent key/suite storage | High — governance changes lost on restart |
| Key-Value Store | ✗ Missing | No RocksDB or equivalent selected | High — must decide before persistence task |
| Audit Trail | ✗ Missing | No timestamped, immutable event log | Medium — regulatory/audit requirements |

Part 6: DevNet → TestNet → MainNet Validation Checklist

6.1 DevNet Gate Criteria (Before Public TestNet)

✓ Crypto Layer
├─ [ ] All T70–T81 tests pass locally
├─ [ ] Suite ID enforcement present (T82)
├─ [ ] No silent fallback on unknown suites
└─ [ ] Multi-suite dispatch verified (test suite only, SHA3)

✓ Consensus & Networking
├─ [ ] HotStuff tick-based loop runs 10+ rounds without crash
├─ [ ] KEMTLS handshake succeeds between 2 peers
├─ [ ] Connection abstraction integrates with eezo-node
└─ [ ] Metrics collected (basic counters, no histograms yet)

✓ Durability (Phase 1 mandatory)
├─ [ ] RocksDB integrated for consensus state
├─ [ ] Node survives 3 restart cycles
├─ [ ] Governance key registry persisted
└─ [ ] Audit log present for all state changes

✓ Testing & Validation
├─ [ ] Unit tests: 95%+ pass rate
├─ [ ] Integration tests: simple 3-node network runs stably
├─ [ ] No memory leaks (sanitizer run: 5 min @ 100k msg/s)
└─ [ ] CodeQL security scan: 0 critical, <5 warning

6.2 TestNet Gate Criteria (Before Public Launch)

✓ Performance (Phase 2 mandatory)
├─ [ ] Single-node load harness deployed
├─ [ ] Toy crypto baseline TPS: >= 1000 TPS (no PQC)
├─ [ ] PQC baseline TPS: >= 500 TPS (SHA3 as PQC proxy)
├─ [ ] E2E latency p50: <= 5 sec, p99: <= 15 sec
└─ [ ] Network metrics exported (queue depth, message rates)

✓ Stability
├─ [ ] 4+ validators run for 1 week without crash
├─ [ ] Network partitions heal within 2 blocks
├─ [ ] State survives 5 full node restarts
└─ [ ] Governance updates apply atomically

✓ Security Audit
├─ [ ] Formal review of T70–T82 complete
├─ [ ] Consensus safety proof reviewed
├─ [ ] Crypto agility design audited
└─ [ ] No known vulnerabilities in deployment scope

6.3 MainNet Gate Criteria (Before Public Launch)

✓ Scalability (Phase 3 mandatory)
├─ [ ] Async runtime (Tokio) integrated and tested
├─ [ ] 20+ validator network runs at >= 1000 TPS
├─ [ ] Latency p99 remains <= 15 sec at full load
├─ [ ] Memory usage stable (no unbounded growth)
└─ [ ] Backpressure handling verified (network saturation test)

✓ Availability
├─ [ ] Peer discovery (bootstrap, seed nodes) deployed
├─ [ ] Block relay and transaction propagation tested
├─ [ ] 100+ node public testnet stable for 4 weeks
└─ [ ] Network survives 30% node churn per round

✓ Final Security & Regulatory
├─ [ ] Full formal audit (external firm) complete
├─ [ ] Penetration testing (consensus attack simulation) passed
├─ [ ] Legal review of PQC implications complete
├─ [ ] Incident response plan documented and tested
└─ [ ] Key custody and validator onboarding procedures approved

✓ Launch Readiness
├─ [ ] Mainnet parameters (block time, validator count, stake) finalized
├─ [ ] Token distribution and genesis block verified
├─ [ ] Exchange/custodian integrations live
└─ [ ] Public communication and audit report published

Part 7: Specific Recommendations

7.1 Immediate Actions (Next 2 Weeks)

- Verify T81 local test results

  - Ensure suite_id fields are in all wire message types

  - Check that existing tests still pass after serialization changes

  - Prepare summary for T82 design

- Start T82 (Suite ID Startup Validation)

  - Add node initialization checks: all suite_ids used by validators must have registered backends

  - Return explicit error (not silent fallback) if suite not found

  - Estimate: 3–5 days

- Assign Phase 1 (Persistence) tasks to OpenAI+Team

  - T83: RocksDB integration (~2 weeks)

  - T84: Governance & audit logging (~1.5 weeks)

  - Gate: DevNet cannot proceed without these

- Schedule Architecture Review

  - 2-hour deep dive on sync vs. async bottleneck

  - Confirm Tokio adoption; agree on channel boundaries

  - Document assumptions for T85 design

7.2 Parallel Workstream Assignments

Team A (Cryptography & Protocol):

- Complete T81 serialization (if not done)

- T82: Suite ID validation

- Prepare T85 async design doc

Team B (DevNet/TestNet Infrastructure):

- T83: RocksDB setup and consensus state persistence

- Network bootstrapping (peer discovery, seed nodes)

- DevNet orchestration (Docker, Kubernetes)

Team C (Performance & Testing):

- T26-style load harness (phase 2)

- Metrics collection and export

- Profile PQC verification overhead

Team D (Integration & Auditing):

- Connect KEMTLS socket layer to eezo-node main loop

- Security review of T70–T81 changes

- Prepare audit scope and formal review schedule

7.3 Risk Mitigation

If Synchronous Bottleneck Discovered Early:

- Fallback: Run DevNet with limited validator set (4–8) to mask latency

- Parallel: Start T85 async design immediately (do not wait)

- Option: Hire performance consultant to profile bottleneck

If Persistence Has Data Corruption:

- Fallback: Add checksums and recovery procedures to T84

- Parallel: Run RocksDB audits before TestNet public

- Option: Use read-only mode initially; enable writes after hardening

If Suite ID Enforcement Breaks Backward Compatibility:

- Fallback: Add deprecation period; support both old (no suite_id) and new (with suite_id) formats

- Parallel: Decide at T82 time whether old nodes can co-exist

- Option: Require coordinated network upgrade (all nodes update simultaneously)

Part 8: Bottleneck Deep Dives

8.1 Synchronous Neck — Technical Root Cause

Current Flow (Pseudocode):

fn main_loop() {
loop {
// Consensus: blocking
consensus.step_once(); // Poll for queued events, run HotStuff, emit votes

// Network: blocking
    network.step_once();     // Send/recv network messages, apply backpressure
    
    // Storage: blocking
    storage.step_once();     // Flush committed blocks to disk
    
    // Overhead: synchronous wait
    // All three must complete before next iteration
    // If any one is slow, the others wait
}

}

Why PQ Signature Verification Makes It Worse:

Consensus work per block:
├─ Verify N proposals (N = validator count)
│ ├─ SHA3 (current): ~100 µs per proposal
│ └─ ML-DSA (future): ~1 ms per proposal (10x worse)
├─ Verify 2N votes (to form QC)
│ ├─ SHA3: ~200 µs total
│ └─ ML-DSA: ~2 ms total
└─ Total per block:
├─ Toy: ~300 µs (negligible)
└─ ML-DSA: ~3 ms (noticeable with 20+ validators)

Block time target (e.g., 2 sec):
├─ With 20 validators, toy crypto: 20 * 3 ms = 60 ms (3% of block time) ✓
└─ With 20 validators, ML-DSA: 20 * 3 ms = 60 ms PLUS network delay, ... → slides to 1.5–1.8 sec actual block time

If consensus miss their slot, HotStuff timeout kicks in → pacemaker advances view → no commit

Solution Approaches:

| Approach | Effort | Benefit | Risk |
| --- | --- | --- | --- |
| Async Runtime (Tokio) | 4 weeks | +1000 TPS possible; all I/O overlapped | Medium — large refactor; must be correct |
| GPU Signature Verification | 6 weeks | PQC verification 10–100x faster | High — complex integration; CUDA/wgpu required |
| Batched Verification | 2 weeks | Amortize PQC overhead; verify in bulk | Medium — changes consensus logic slightly |
| Caching / Session Reuse | 1 week | Avoid re-verify same votes in timeouts | Low — incremental, minimal risk |

Recommended Priority: Async (T85–T86) first; GPU as optional acceleration in parallel

8.2 Persistence Gap — Safety Implications

HotStuff Safety Invariant (From Moniz et al. 2020):

A node that locks a block must not vote for any conflicting block in a later view.

Current Problem (RAM-only state):

View 1: Node A locks block B1 (stores in memory)
View 2: Node A crashes
(locked block B1 lost)
View 3: Node A restarts, no state
(doesn't remember B1 is locked)
View 4: Network asks A to vote for B2 (conflicts with B1)
(A votes, thinking no lock exists)

Result: Safety violation — conflicting blocks both got quorum support

DevNet Impact (Low Severity):

- Single machine or lab environment; orchestration can force ordered restarts

- No real money at risk; failures are benign

TestNet Impact (High Severity):

- Multi-cloud deployment; nodes restart independently

- Validators may crash from network issues; restart without waiting

- First observed consensus safety failure on TestNet could discredit the project

MainNet Impact (Critical):

- Unacceptable; violates fundamental safety invariant

- Auditors and exchanges will not accept non-durable consensus state

- Legal liability if funds are lost due to equivocation

Recovery Path:

- T83: Consensus State Durability

  - Log every lock decision (view, block hash, lock proof) to disk before accepting votes

  - Recover lock state on restart; refuse votes on conflicting blocks

- T84: Audit Trail

  - Timestamped log of all state changes

  - Allows external auditors to verify consensus safety post-hoc

8.3 Protocol Lag — Upgrade Coordination

Example: Rolling Out ML-DSA

Time T0 (baseline):
├─ All validators use SUITETOYSHA3 (suite_id = 0)
├─ Governance lists all validators with suite 0
└─ Wire format: vote.suite_id = 0

Time T0 + 1 week (50% validators upgraded):
├─ First 50 validators: SUITEMLDS A (suite_id = 1)
├─ Last 50 validators: SUITETOYSHA3 (suite_id = 0)
├─ Network must now accept both suites

Time T0 + 2 weeks (100% upgraded):
├─ All validators: SUITEMLDSAA
├─ Governance transitions to suite 1
└─ Decommission suite 0

Failure scenario WITHOUT T82:
├─ Old node version doesn't recognize suite_id on wire
├─ Falls back to hardcoded SUITETOYSHA3
├─ Receives vote with suite_id = 1 (ML-DSA)
├─ Tries to verify using SHA3 backend → fails
├─ Rejects all votes from upgraded validators
└─ Network partitions (old vs. new)

With T82 (Suite ID Validation):
├─ Old node sees suite_id = 1 on wire
├─ Queries backend registry
├─ Backend not registered → explicit error
├─ Node refuses to start (or safe shutdown)
└─ Operator is forced to upgrade (not silent failure)

Upgrade Protocol (Post-T82):

- Governance announces suite 1 support (blockchain tx)

- Validators who support suite 1 enable backend & update their key registration

- Network reaches epoch boundary

- All nodes must have suite 1 backend registered before epoch starts

- Suite 0 support deprecated; nodes refusing to run with suite 0 only

Part 9: OpenAI Collaboration Scope & Recommendations

9.1 Proposed Collaboration Model

Based on conversation logs, OpenAI is providing:

- GitHub AI agent (Devin-like) for code implementation

- Architectural guidance and task breakdown

- Integration and testing support

Recommended Focus Areas for Partnership:

- Phase 1 (Weeks 1–4): Persistence & Protocol

  - Assign T82–T84 to OpenAI team

  - Your team: RocksDB schema design, governance persistence API

  - OpenAI: Implementation, testing, integration with cano-consensus

- Phase 2 (Weeks 5–8): Observability & Load Testing

  - Assign T26-style metrics and load harness to OpenAI

  - Your team: Metrics design, benchmark targets

  - OpenAI: Implementation, Prometheus integration, harness tooling

- Phase 3 (Weeks 9–14): Async Refactor

  - Critical: You define async boundaries (T85) before OpenAI codes

  - Assign T86a (consensus), T86b (network), T86c (storage) to OpenAI in parallel

  - Your team: Code review, integration testing, performance validation

9.2 Governance of Collaboration

Decision Points:

- [ ] Does OpenAI have production deployment authority? (No — recommend review gates)

- [ ] How are breaking changes handled? (Propose: change proposals must pass audit)

- [ ] Who owns final TestNet/MainNet decision? (Recommend: joint with external auditor)

- [ ] What's the escalation path for security findings? (Recommend: pause deployment, fix, re-audit)

Recommendation: Establish a steering committee (You + OpenAI + external security auditor) that gates major changes before TestNet/MainNet

Part 10: Audit Report Summary & Conclusion

10.1 Overall Assessment

| Dimension | Rating | Notes |
| --- | --- | --- |
| Cryptographic Design | A | Multi-suite framework sound; algorithm-agnostic; minor enforcement gaps (T82) |
| Consensus Logic | A | HotStuff correct; observability minimal; sync bottleneck will appear under load |
| Networking | B | KEMTLS ready; P2P infrastructure incomplete (peer discovery, backpressure) |
| Durability | D | Critical gap; must fix before TestNet |
| Performance | Unrated | No benchmarks; expected 500–1000 TPS with toy crypto; PQC impact unknown |
| Operational Readiness | C | DevNet feasible; TestNet risky without Phase 1; MainNet requires Phase 1–3 complete |

10.2 Go / No-Go Recommendations

| Environment | Current Status | Recommendation | Condition |
| --- | --- | --- | --- |
| DevNet | Ready | ✅ Proceed | Complete T82; run for 1 week stability test |
| TestNet Public | Not Ready | 🛑 Hold | Wait for Phase 1 (T82–T84) + Phase 2 (metrics/load) |
| MainNet | Not Ready | 🛑 Hold | Wait for Phase 1–3 complete + formal security audit |

10.3 Estimated Timeline to Production

Optimistic (All teams aligned, no blockers):

- Phase 1: 4.5 weeks → DevNet launch

- Phase 2: 5.5 weeks → TestNet public launch

- Phase 3: 7.5 weeks → MainNet ready (~ 17 weeks from now, late May 2026)

Realistic (Normal blockers, 30% schedule margin):

- Phase 1: 6 weeks

- Phase 2: 7 weeks

- Phase 3: 10 weeks

- Estimated MainNet: July 2026 (25 weeks from now)

Pessimistic (Major rework, performance surprises):

- Add 8–12 weeks for async refactor if bottleneck is worse than expected

- Add 4–6 weeks for governance key rotation protocol if design changes

- Estimated MainNet: September–October 2026 (40+ weeks from now)

10.4 Key Success Factors

- Complete Phase 1 on schedule — Persistence is blocking everything downstream

- Lock async design (T85) early — Prevents rework in T86

- Load test continuously — Discover bottlenecks incrementally; don't wait for TestNet

- Schedule formal security audit — Parallel to implementation; results inform fixes

- Communicate with validators & exchanges — Set expectations; avoid launch date surprises

References & Further Reading

Canonical Sources (From Project Logs)

- T0 conversation: Full project history, task breakdowns, design decisions

- T26: Network runtime observability proposal

- T70–T81: Cryptographic infrastructure completion

- T82–T85: Proposed future tasks (not yet started)

External Sources

- "A Scalable Post Quantum Secure Blockchain Framework with Adaptive Consensus" (Nature, 2025) — Post-quantum blockchain scaling insights

- NIST Post-Quantum Cryptography Standards (2022) — Algorithm agility design patterns

- HotStuff Consensus Paper (Moniz et al., 2020) — Safety and liveness invariants

- Devnet vs Testnet vs Mainnet (GatewayFM, 2024) — Deployment stage criteria

Appendix A: Crypto Suite ID Mapping (Reference)

Current (T81 Local):
├─ SUITETOYSHA3 = 0 (test-only SHA3 backend)
└─ Reserved for future PQ:
├─ SuiteID(1) = ML-DSA (planned)
├─ SuiteID(2) = SPHINCS+ (planned)
├─ SuiteID(3) = Falcon (optional)
└─ SuiteID(4–65535) = Reserved for future

Mapping Status:
├─ Wire format: Suite ID should be in all Vote/Proposal/QC messages (T81 added locally)
├─ Enforcement: Missing until T82 (startup validation)
├─ Rotation protocol: Defined at T82 time or later (T82+ spec)
└─ Backward compatibility: Not yet addressed (T82+ spec)

Appendix B: Checklist for Next Leadership Meeting

- [ ] Review Phase 1 timeline; confirm team capacity

- [ ] Approve Tokio async decision for T85; document assumptions

- [ ] Schedule formal security audit; select external firm

- [ ] Assign DevNet/TestNet infrastructure leads

- [ ] Confirm OpenAI collaboration scope & governance

- [ ] Set public communication (when will EEZO announce DevNet launch?)

- [ ] Review validator onboarding & key management procedures

- [ ] Discuss token economics & exchange integration timeline

End of Report

This audit reflects the project status as of January 15, 2026, based on 143+ conversations and 81+ development tasks (T0–T81). Recommendations assume continued OpenAI partnership and dedicated team engagement.

EEZO Post-Quantum Cryptography Blockchain

Comprehensive Architecture, Plan & Audit Report

Prepared for: EEZO Blockchain Project + OpenAI Partnership
Prepared by: Technical Audit Team
Date: January 15, 2026
Status: Confidential - Development Phase Review

Executive Summary

This audit evaluates the EEZO blockchain project's architecture, design, implementation status, and strategic bottlenecks across parallel DevNet/TestNet/MainNet development pipelines. The assessment covers cryptographic infrastructure (T70–T81), consensus mechanisms (HotStuff BFT), networking (KEMTLS post-quantum handshake), and identifies critical gaps preventing production readiness.

Key Findings

Strengths:

- Multi-suite cryptographic governance framework (T79–T80) provides foundational agility for PQ algorithm rotation

- KEMTLS post-quantum handshake implementation (T24–T27) enables secure peer-to-peer connections

- Comprehensive test-driven development with per-task validation gates

- Algorithm-agnostic consensus verifier design maintains future flexibility

Critical Gaps:

- Synchronous Bottleneck — Step-once polling loop blocks TPS scalability and latency targets

- Persistence Gap — RAM-only state violates consensus safety invariants; no durable consensus logs

- Protocol Serialization Gap — Suite IDs not carried on wire; suite rotation fragile and uncoordinated

- Network Runtime Observability — Missing metrics for consensus message rates, queue backpressure, and async overhead

- Load Testing Absence — No scriptable harness to measure node throughput, latency under realistic PQC verification loads

Parallel Deployment Risk:
Developing DevNet/TestNet/MainNet in parallel without foundational persistence or observability creates validation blindness—bugs discovered late in one environment may require architectural rewrites affecting all three.

Part 1: Project Status & Completed Work

1.1 Completed Cryptographic Infrastructure (T70–T81)

Task Sequence Overview

| Task | Title | Status | Outcome |
| --- | --- | --- | --- |
| T70 | Consensus Key Registry & Governance | ✓ Complete | Multi-validator key lookup via traits; governance integration ready |
| T71–T75 | (Prior crypto foundation work) | ✓ | HKDF session keys, AEAD encryption, algorithm-agnostic design |
| T76 | Consensus Signature Verification Trait | ✓ | ConsensusSigVerifier trait, algorithm-agnostic, test SHA3 backend |
| T77 | Multi-Suite Traits & Governance Bridge | ✓ | GovernedValidatorKeyRegistry connects governance to validation |
| T78 | Metrics & Debug Logging for Consensus Sig | ✓ | Per-validator, per-kind metrics; confidential logging (no key/sig data) |
| T79 | Multi-Suite Consensus Key Governance | ✓ | ConsensusSigSuiteId opaque type; SuiteAwareValidatorKeyProvider; per-suite dispatch ready |
| T80 | Integrate MultiSuiteCryptoVerifier | ✓ | Single-backend verifier now delegates to multi-suite; HotStuff driver unified |
| T81 | Carry SuiteId on Wire & Records | ✓ Local Tests | ConsensusSigSuiteId propagated to Vote, Proposal, QC structures; serialization ready |

What These Tasks Achieved

- Algorithm Agnosticism — ConsensusSigVerifier trait does not hardcode crypto algorithms; suite IDs allow future PQ plugging (ML-DSA, SPHINCS+, SLH-DSA, etc.)

- Multi-Suite Governance — Validators can use different signature suites; governance returns suite ID + public key bytes per validator

- Per-Suite Verification Dispatch — MultiSuiteCryptoVerifier looks up the appropriate backend (SHA3 test suite today) and verifies accordingly

- Metrics & Observability — Vote/proposal verification success/failure counts, missing-key detection, latency hooks in place

- Wire Format Readiness (T81) — Suite IDs now part of consensus message structures, but not yet enforced on actual network transport

Current Bottleneck: Suite ID Enforcement & Upgrade Path

- Issue: SuiteIds are in data structures but not yet validated at node startup (T82 was proposed for startup-time checks)

- Risk: Unknown suite ID in a received vote/proposal defaults to generic VerificationErrorOther; no per-suite version negotiation

- Impact: Hybrid transitions (rolling out new PQ suites while running old ones) lack explicit coordination or error reporting

1.2 Consensus & Network Layer (HotStuff + KEMTLS)

HotStuff BFT with Pacemaker

- Status: Implemented and tested (per T0 conversation logs)

- Current: Tick-based synchronous polling loop; commit pruning active

- Missing: Async/await integration; no runtime observability

KEMTLS Post-Quantum Handshake (T24–T27)

- Completed: Stateless cookie mechanism, ClientInit/ServerCookie/ServerAccept flow

- Scope: eezo-net crate, pure-logic cryptographic handshake (no sockets/async yet)

- What Works: Session key derivation, encrypted transport frame format, test coverage for cookie, signature, suite mismatches

- What's Missing: Real socket integration in eezo-node; no async TLS state machine in production path

Connection Orchestration (T28)

- Status: Logical Connection abstraction ready (hands byte frames in/out)

- Scope: Still pure logic; no socket I/O

- Next: Integrate with actual TCP peer-to-peer layer (currently in eezo-node but not tested under load)

Part 2: Strategic Bottlenecks (The Three Necks)

2.1 The Synchronous Neck — Step-Once Polling Loop

Problem:
Current architecture:
┌─────────────────────────────┐
│ eezo-node main loop │
├─────────────────────────────┤
│ while running: │
│ consensus.step_once() │
│ network.step_once() │
│ storage.step_once() │
│ // block until all done │
└─────────────────────────────┘

Why It Bottlenecks TPS & Latency:

- Wasted Wakeups — If consensus has nothing to do, CPU spins waiting for network; network I/O blocks on storage commit

- No Overlapping I/O — Consensus verification waits for network message arrival; network waits for storage ACK before polling again

- PQ Verification Overhead — Verifying ML-DSA or SPHINCS+ signatures (larger signatures than ECC) in a synchronous loop increases worst-case block latency

- Validator Scheduling Fragility — Proposers miss their slot if consensus + disk commit takes longer than block time

Current Measurement:

- No instrumentation yet (T78 metrics are present but not aggregated for end-to-end latency)

- Load harness missing (proposed in T26 context but not built)

Impact on Parallel Deployments:

- DevNet may run fine with 1–10 validators (synchronous overhead masked)

- TestNet with 50+ validators will show degraded block times; MainNet targets unachievable without async

Required Fix:
Move to Tokio async runtime with:

- Async consensus loop (awaiting network messages, storage commits)

- Non-blocking signature verification (GPU-accelerated PQ verification offload)

- Channels and task boundaries (consensus ↔ network ↔ storage decoupled)

Proposed Task: T85 (Design async boundaries; T86+ incremental refactors)

2.2 The Persistence Gap — RAM-Only State

Current State:
Consensus State:
├─ Locked QC (in memory)
├─ Last vote (in memory)
├─ Pacemaker view (in memory)
└─ No persistent log

Ledger State:
├─ Blocks (maybe in memory)
├─ Transactions (maybe in memory)
├─ Balances (memory)
├─ Governance Key Registry (memory)
└─ No on-disk backup

On Node Restart:
├─ All state lost
├─ Cannot rejoin or prove safety history
└─ Audit trail evaporates

Why This Violates Consensus Safety:

- Liveness Assumption Broken — HotStuff assumes nodes remember votes; restart causes equivocation risk if votes aren't durable

- Recovery Undefined — No replay or state rebuilding path; nodes restart from genesis each time (if that works at all)

- Audit Impossibility — No persistent history of decisions; external auditors cannot verify consensus correctness

Impact on Parallel Deployments:

| Environment | Issue | Severity |
| --- | --- | --- |
| DevNet | Crashes lose all state; manual restart required | Medium |
| TestNet | Network instability + state loss = unrecoverable partitions | High |
| MainNet | Unacceptable; violates custody and regulatory requirements | Critical |

Required Fixes (Proposed T83–T84):

- T83: RocksDB-backed persistence layer; trait-based storage abstraction

- T84: Governance key registry persistence; consensus QC/vote logging; auditable ledger state

Estimated Scope:

- 3–5 tasks to make persistence correct and fast

- Must precede TestNet launch

2.3 The Protocol Lag — Suite IDs Not on Wire

Current State:
Wire Format (After T81, not yet deployed):
Vote {
validator_id: u64,
suite_id: ConsensusSigSuiteId, // ← Added in T81 locally
signature: Vec<u8>,
...
}

But in ACTUAL network transmission:

- suite_id may not be serialized yet (depends on codec)

- Or suite_id IS serialized but receiver ignores it

- Or no backward compatibility story if suite_id missing in old messages

Why This Prevents Upgrade Coordination:

- Silent Fallback — If suite_id missing on wire, verifier defaults to SUITETOYSHA3; hides misconfiguration

- No Version Negotiation — When rolling out ML-DSA, no explicit handshake to agree on suite; nodes may quietly verify with wrong algorithm

- Audit Fragility — External bridges/validators cannot reconstruct which suite was used for a vote months after the fact

Example Failure Scenario:
Time T0: Network uses ML-DSA (suite ID 1)
Time T0 + 3 months: Maintainer accidentally deploys with old binary (suite ID 0, SHA3)
Time T0 + 3 months, block N:

- Votes from suite 1 nodes arrive

- Old binary sees no suite_id on wire (backward compat broken)

- Defaults to suite 0, verification fails

- Network halts, consensus dead

Required Fixes (T82, not yet started):

- Ensure suite_id is always on the wire in canonical form

- Reject unknown suite IDs explicitly (not silent fallback)

- Add startup validation that all in-use suite IDs have registered backends

Estimated Scope: 1–2 tasks

Part 3: Architecture Gaps & Blockers

3.1 Network Runtime Observability (Missing from T78–T81)

What Exists (T78 added to CryptoConsensusVerifier):

- Signature verification success/failure counts

- Missing-key detection

- Per-validator, per-message-kind counters

What's Missing:
From T26 context, the original proposal included:

Planned but not yet built:

Part A: Network runtime metrics
├─ Inbound consensus message rates (by kind: vote, proposal, other)
├─ Outbound message rates
├─ Queue occupancy on consensus event channel
├─ spawnblocking usage count and latency
└─ Async node runtime visibility

Part B: Load harness
├─ Single-node load harness (loopback network)
├─ Configurable message injection (votes, proposals)
├─ Prometheus or simple metrics export
└─ Latency histograms (e2e consensus tick)

Why This Matters:

- Without metrics, cannot measure impact of PQ signature verification on throughput

- Cannot diagnose network backpressure under load

- Cannot correlate performance regressions to code changes

Blocking: Tuning for TestNet/MainNet TPS targets

3.2 Load Testing & Performance Validation (Absent)

Missing Tooling:

- No scriptable harness to stress a single node with configurable consensus messages

- No end-to-end latency measurement (proposal submit → committed block)

- No throughput (TPS) baseline for different validator set sizes

- No performance data for ML-DSA, SPHINCS+ signature verification under realistic loads

Current Situation:

- Unit tests pass (per conversation logs)

- No integration tests under network load

- No profile data showing bottleneck (crypto, network, or consensus logic)

Why This Blocks Parallel Deployment:

- DevNet may be "complete" but hitting 1000 TPS is unknown

- TestNet could have undiscovered scaling issues (too late in the pipeline)

- MainNet launch risks hitting performance regression post-deployment

Estimated Effort:

- T26 proposed a straightforward load harness (2–3 tasks)

- Performance profiling (1–2 tasks)

3.3 Governance & Key Rotation Automation (Minimal)

Current State:

- Governance trait returns suite_id + public key bytes per validator

- Suite ID is u16 opaque type (no versioning, no deprecation)

- No explicit key rotation or suite upgrade protocol

What's Missing:

- Mechanism to announce key changes to the network

- Transition period (old + new keys valid simultaneously)

- Explicit "suite A → suite B" protocol

- Validator coordination during rollout

Risk:

- Changing a validator's key in governance may be silent; no network agreement

- Possible acceptance of old votes after key change (if timestamps not checked)

- Difficult audit trail (when did each validator change suites?)

Estimated Scope: 1–2 design tasks + 3–4 implementation tasks (post-launch)

Part 4: Parallel Deployment Strategy Assessment

4.1 Recommended Timeline

Phase 1: Persistence & Protocol Hardening (Weeks 1–4)

Critical Path for TestNet

| Task | Effort | Blocker | Description |
| --- | --- | --- | --- |
| T82 | 1 week | (T81) | Startup validation: all suite_ids have backends; error on unknown suites |
| T83 | 2 weeks | (T82) | RocksDB integration; consensus state durability |
| T84 | 1.5 weeks | (T83) | Governance key registry persistence; audit logging |
| Subtotal | 4.5 weeks | — | Enables TestNet to survive restarts & run audits |

Phase 2: Observability & Load Testing (Weeks 5–8)

Required Before TestNet Public

| Task | Effort | Blocker | Description |
| --- | --- | --- | --- |
| Metrics (T26 proposal) | 1 week | (T78) | Network runtime counters; queue depth; async overhead |
| Load Harness | 1.5 weeks | (T27 transport) | Single-node loopback; configurable message injection; TPS measurement |
| Performance Baseline | 1 week | (Load harness) | Run with toy crypto; measure e2e latency, throughput |
| PQC Perf Profiling | 2 weeks | (Load harness) | Insert ML-DSA verification; measure throughput regression |
| Subtotal | 5.5 weeks | — | Unblocks TestNet TPS validation; reveals bottlenecks |

Phase 3: Async Transition Design & P2P Integration (Weeks 9–14)

Long-lead for MainNet Performance

| Task | Effort | Blocker | Description |
| --- | --- | --- | --- |
| T85 Async Design | 2 weeks | (All Phase 1–2) | Define Tokio task boundaries; consensus ↔ network ↔ storage; channel design |
| T86a Async Consensus | 2 weeks | (T85) | Move consensus step into async; handle message subscriptions |
| T86b Async Network | 2 weeks | (T85) | TCP sockets + KEMTLS handshake in Tokio; backpressure handling |
| T86c Async Storage | 1.5 weeks | (T85) | RocksDB async I/O; buffer consensus writes |
| Subtotal | 7.5 weeks | — | Foundational scalability; ready for MainNet performance targets |

4.2 Risk Matrix: Parallel vs. Sequential Approach

Parallel (Current Plan) — DevNet, TestNet, MainNet in parallel

Timeline Advantage: +8 weeks (all three launch sooner)

Risk/Cost:
├─ Synchronous Neck unknown in DevNet → surprised by in TestNet
├─ Persistence Gap not visible until TestNet crash → MainNet unprepared
├─ Protocol Lag delays upgrade testing → coordination issues at launch
├─ Load Testing absent → MainNet performance unknown until live
├─ Audit review on three codebases in parallel → review fatigue, missed issues
└─ Rollback complexity if Phase 1 issues discovered late

Sequential (Fallback Recommendation) — DevNet → TestNet → MainNet, strict gates

Timeline Penalty: +8 weeks (sequential, but each environment fully validated)

Risk Reduction:
├─ DevNet findings apply to TestNet design (no surprises)
├─ TestNet persistence fully proven before MainNet
├─ Protocol upgrades tested on TestNet before MainNet rollout
├─ Load testing identifies bottlenecks; fixes integrated before MainNet
├─ Single codebase review → higher quality
└─ Clear exit criteria for each gate

Recommended Hybrid (Optimal):

- Finish Phase 1 (Persistence, T82–T84) before DevNet launch — All three can start in parallel after this

- Complete Phase 2 (Observability, T26 + Load harness) before TestNet public — Don't launch TestNet blind

- Start Phase 3 (Async) in TestNet beta — Incremental rollout, measure impact

- MainNet gates: All Phase 1–3 complete, 4+ weeks public TestNet stability, formal audit passed

Part 5: Detailed Gap Analysis

5.1 Cryptographic Stack

| Component | Status | Gaps | Risk |
| --- | --- | --- | --- |
| Algorithm Agnosticism | ✓ Complete | Suite ID enforcement missing (T82) | Medium — silent fallback on wire |
| Multi-Suite Governance | ✓ Complete | No key rotation protocol | High — validator suite changes fragile |
| KEMTLS Handshake | ✓ Logic ready | No socket integration; no async | Medium — peer-to-peer untested under load |
| Session Keys (HKDF) | ✓ Complete | No session reuse/caching | Low — correctness fine, perf improvable |
| AEAD Encryption | ✓ Complete | No authenticated frames for malicious peer detection | Low — not required for correctness |

5.2 Consensus (HotStuff)

| Component | Status | Gaps | Risk |
| --- | --- | --- | --- |
| Core Algorithm | ✓ Complete | Synchronous bottleneck; no backpressure handling | High — TPS ceiling unknown |
| Metrics | ✓ Partial | No e2e latency, throughput histograms | High — cannot diagnose performance issues |
| State Persistence | ✗ Missing | RAM-only; no recovery | Critical — violates safety invariants |
| Network Observability | ✗ Missing | No queue depth, message rate metrics | High — cannot tune network stack |
| Load Harness | ✗ Missing | No scriptable testing; manual load only | High — undiscovered bottlenecks |

5.3 Networking (KEMTLS + P2P)

| Component | Status | Gaps | Risk |
| --- | --- | --- | --- |
| KEMTLS Logic | ✓ Complete | No real TCP socket integration | Medium — assumed to work, untested |
| Connection Abstraction | ✓ Complete | Pure logic, no async I/O | High — synchronous wrapper needed |
| Peer Discovery | ✗ Missing | No bootstrap, seed node, peer routing | Critical — isolated nodes cannot find peers |
| Message Propagation | ✗ Missing | No mempool, block relay, gossip | Critical — consensus cannot advance |
| Backpressure Handling | ✗ Missing | No flow control; unbounded channel growth | High — network stalls under high load |

5.4 Storage & Durability

| Component | Status | Gaps | Risk |
| --- | --- | --- | --- |
| Consensus State Logging | ✗ Missing | No QC, vote, proposal persistence | Critical — consensus safety violated on restart |
| Ledger State | ✗ Missing | No block/transaction durability | Critical — cannot verify chain after restart |
| Governance Registry | ✗ Missing | No persistent key/suite storage | High — governance changes lost on restart |
| Key-Value Store | ✗ Missing | No RocksDB or equivalent selected | High — must decide before persistence task |
| Audit Trail | ✗ Missing | No timestamped, immutable event log | Medium — regulatory/audit requirements |

Part 6: DevNet → TestNet → MainNet Validation Checklist

6.1 DevNet Gate Criteria (Before Public TestNet)

✓ Crypto Layer
├─ [ ] All T70–T81 tests pass locally
├─ [ ] Suite ID enforcement present (T82)
├─ [ ] No silent fallback on unknown suites
└─ [ ] Multi-suite dispatch verified (test suite only, SHA3)

✓ Consensus & Networking
├─ [ ] HotStuff tick-based loop runs 10+ rounds without crash
├─ [ ] KEMTLS handshake succeeds between 2 peers
├─ [ ] Connection abstraction integrates with eezo-node
└─ [ ] Metrics collected (basic counters, no histograms yet)

✓ Durability (Phase 1 mandatory)
├─ [ ] RocksDB integrated for consensus state
├─ [ ] Node survives 3 restart cycles
├─ [ ] Governance key registry persisted
└─ [ ] Audit log present for all state changes

✓ Testing & Validation
├─ [ ] Unit tests: 95%+ pass rate
├─ [ ] Integration tests: simple 3-node network runs stably
├─ [ ] No memory leaks (sanitizer run: 5 min @ 100k msg/s)
└─ [ ] CodeQL security scan: 0 critical, <5 warning

6.2 TestNet Gate Criteria (Before Public Launch)

✓ Performance (Phase 2 mandatory)
├─ [ ] Single-node load harness deployed
├─ [ ] Toy crypto baseline TPS: >= 1000 TPS (no PQC)
├─ [ ] PQC baseline TPS: >= 500 TPS (SHA3 as PQC proxy)
├─ [ ] E2E latency p50: <= 5 sec, p99: <= 15 sec
└─ [ ] Network metrics exported (queue depth, message rates)

✓ Stability
├─ [ ] 4+ validators run for 1 week without crash
├─ [ ] Network partitions heal within 2 blocks
├─ [ ] State survives 5 full node restarts
└─ [ ] Governance updates apply atomically

✓ Security Audit
├─ [ ] Formal review of T70–T82 complete
├─ [ ] Consensus safety proof reviewed
├─ [ ] Crypto agility design audited
└─ [ ] No known vulnerabilities in deployment scope

6.3 MainNet Gate Criteria (Before Public Launch)

✓ Scalability (Phase 3 mandatory)
├─ [ ] Async runtime (Tokio) integrated and tested
├─ [ ] 20+ validator network runs at >= 1000 TPS
├─ [ ] Latency p99 remains <= 15 sec at full load
├─ [ ] Memory usage stable (no unbounded growth)
└─ [ ] Backpressure handling verified (network saturation test)

✓ Availability
├─ [ ] Peer discovery (bootstrap, seed nodes) deployed
├─ [ ] Block relay and transaction propagation tested
├─ [ ] 100+ node public testnet stable for 4 weeks
└─ [ ] Network survives 30% node churn per round

✓ Final Security & Regulatory
├─ [ ] Full formal audit (external firm) complete
├─ [ ] Penetration testing (consensus attack simulation) passed
├─ [ ] Legal review of PQC implications complete
├─ [ ] Incident response plan documented and tested
└─ [ ] Key custody and validator onboarding procedures approved

✓ Launch Readiness
├─ [ ] Mainnet parameters (block time, validator count, stake) finalized
├─ [ ] Token distribution and genesis block verified
├─ [ ] Exchange/custodian integrations live
└─ [ ] Public communication and audit report published

Part 7: Specific Recommendations

7.1 Immediate Actions (Next 2 Weeks)

- Verify T81 local test results

  - Ensure suite_id fields are in all wire message types

  - Check that existing tests still pass after serialization changes

  - Prepare summary for T82 design

- Start T82 (Suite ID Startup Validation)

  - Add node initialization checks: all suite_ids used by validators must have registered backends

  - Return explicit error (not silent fallback) if suite not found

  - Estimate: 3–5 days

- Assign Phase 1 (Persistence) tasks to OpenAI+Team

  - T83: RocksDB integration (~2 weeks)

  - T84: Governance & audit logging (~1.5 weeks)

  - Gate: DevNet cannot proceed without these

- Schedule Architecture Review

  - 2-hour deep dive on sync vs. async bottleneck

  - Confirm Tokio adoption; agree on channel boundaries

  - Document assumptions for T85 design

7.2 Parallel Workstream Assignments

Team A (Cryptography & Protocol):

- Complete T81 serialization (if not done)

- T82: Suite ID validation

- Prepare T85 async design doc

Team B (DevNet/TestNet Infrastructure):

- T83: RocksDB setup and consensus state persistence

- Network bootstrapping (peer discovery, seed nodes)

- DevNet orchestration (Docker, Kubernetes)

Team C (Performance & Testing):

- T26-style load harness (phase 2)

- Metrics collection and export

- Profile PQC verification overhead

Team D (Integration & Auditing):

- Connect KEMTLS socket layer to eezo-node main loop

- Security review of T70–T81 changes

- Prepare audit scope and formal review schedule

7.3 Risk Mitigation

If Synchronous Bottleneck Discovered Early:

- Fallback: Run DevNet with limited validator set (4–8) to mask latency

- Parallel: Start T85 async design immediately (do not wait)

- Option: Hire performance consultant to profile bottleneck

If Persistence Has Data Corruption:

- Fallback: Add checksums and recovery procedures to T84

- Parallel: Run RocksDB audits before TestNet public

- Option: Use read-only mode initially; enable writes after hardening

If Suite ID Enforcement Breaks Backward Compatibility:

- Fallback: Add deprecation period; support both old (no suite_id) and new (with suite_id) formats

- Parallel: Decide at T82 time whether old nodes can co-exist

- Option: Require coordinated network upgrade (all nodes update simultaneously)

Part 8: Bottleneck Deep Dives

8.1 Synchronous Neck — Technical Root Cause

Current Flow (Pseudocode):

fn main_loop() {
loop {
// Consensus: blocking
consensus.step_once(); // Poll for queued events, run HotStuff, emit votes

// Network: blocking
    network.step_once();     // Send/recv network messages, apply backpressure
    
    // Storage: blocking
    storage.step_once();     // Flush committed blocks to disk
    
    // Overhead: synchronous wait
    // All three must complete before next iteration
    // If any one is slow, the others wait
}

}

Why PQ Signature Verification Makes It Worse:

Consensus work per block:
├─ Verify N proposals (N = validator count)
│ ├─ SHA3 (current): ~100 µs per proposal
│ └─ ML-DSA (future): ~1 ms per proposal (10x worse)
├─ Verify 2N votes (to form QC)
│ ├─ SHA3: ~200 µs total
│ └─ ML-DSA: ~2 ms total
└─ Total per block:
├─ Toy: ~300 µs (negligible)
└─ ML-DSA: ~3 ms (noticeable with 20+ validators)

Block time target (e.g., 2 sec):
├─ With 20 validators, toy crypto: 20 * 3 ms = 60 ms (3% of block time) ✓
└─ With 20 validators, ML-DSA: 20 * 3 ms = 60 ms PLUS network delay, ... → slides to 1.5–1.8 sec actual block time

If consensus miss their slot, HotStuff timeout kicks in → pacemaker advances view → no commit

Solution Approaches:

| Approach | Effort | Benefit | Risk |
| --- | --- | --- | --- |
| Async Runtime (Tokio) | 4 weeks | +1000 TPS possible; all I/O overlapped | Medium — large refactor; must be correct |
| GPU Signature Verification | 6 weeks | PQC verification 10–100x faster | High — complex integration; CUDA/wgpu required |
| Batched Verification | 2 weeks | Amortize PQC overhead; verify in bulk | Medium — changes consensus logic slightly |
| Caching / Session Reuse | 1 week | Avoid re-verify same votes in timeouts | Low — incremental, minimal risk |

Recommended Priority: Async (T85–T86) first; GPU as optional acceleration in parallel

8.2 Persistence Gap — Safety Implications

HotStuff Safety Invariant (From Moniz et al. 2020):

A node that locks a block must not vote for any conflicting block in a later view.

Current Problem (RAM-only state):

View 1: Node A locks block B1 (stores in memory)
View 2: Node A crashes
(locked block B1 lost)
View 3: Node A restarts, no state
(doesn't remember B1 is locked)
View 4: Network asks A to vote for B2 (conflicts with B1)
(A votes, thinking no lock exists)

Result: Safety violation — conflicting blocks both got quorum support

DevNet Impact (Low Severity):

- Single machine or lab environment; orchestration can force ordered restarts

- No real money at risk; failures are benign

TestNet Impact (High Severity):

- Multi-cloud deployment; nodes restart independently

- Validators may crash from network issues; restart without waiting

- First observed consensus safety failure on TestNet could discredit the project

MainNet Impact (Critical):

- Unacceptable; violates fundamental safety invariant

- Auditors and exchanges will not accept non-durable consensus state

- Legal liability if funds are lost due to equivocation

Recovery Path:

- T83: Consensus State Durability

  - Log every lock decision (view, block hash, lock proof) to disk before accepting votes

  - Recover lock state on restart; refuse votes on conflicting blocks

- T84: Audit Trail

  - Timestamped log of all state changes

  - Allows external auditors to verify consensus safety post-hoc

8.3 Protocol Lag — Upgrade Coordination

Example: Rolling Out ML-DSA

Time T0 (baseline):
├─ All validators use SUITETOYSHA3 (suite_id = 0)
├─ Governance lists all validators with suite 0
└─ Wire format: vote.suite_id = 0

Time T0 + 1 week (50% validators upgraded):
├─ First 50 validators: SUITEMLDSAA (suite_id = 1)
├─ Last 50 validators: SUITETOYSHA3 (suite_id = 0)
├─ Network must now accept both suites

Time T0 + 2 weeks (100% upgraded):
├─ All validators: SUITEMLDSAA
├─ Governance transitions to suite 1
└─ Decommission suite 0

Failure scenario WITHOUT T82:
├─ Old node version doesn't recognize suite_id on wire
├─ Falls back to hardcoded SUITETOYSHA3
├─ Receives vote with suite_id = 1 (ML-DSA)
├─ Tries to verify using SHA3 backend → fails
├─ Rejects all votes from upgraded validators
└─ Network partitions (old vs. new)

With T82 (Suite ID Validation):
├─ Old node sees suite_id = 1 on wire
├─ Queries backend registry
├─ Backend not registered → explicit error
├─ Node refuses to start (or safe shutdown)
└─ Operator is forced to upgrade (not silent failure)

Upgrade Protocol (Post-T82):

- Governance announces suite 1 support (blockchain tx)

- Validators who support suite 1 enable backend & update their key registration

- Network reaches epoch boundary

- All nodes must have suite 1 backend registered before epoch starts

- Suite 0 support deprecated; nodes refusing to run with suite 0 only

Part 9: OpenAI Collaboration Scope & Recommendations

9.1 Proposed Collaboration Model

Based on conversation logs, OpenAI is providing:

- GitHub AI agent (Devin-like) for code implementation

- Architectural guidance and task breakdown

- Integration and testing support

Recommended Focus Areas for Partnership:

- Phase 1 (Weeks 1–4): Persistence & Protocol

  - Assign T82–T84 to OpenAI team

  - Your team: RocksDB schema design, governance persistence API

  - OpenAI: Implementation, testing, integration with cano-consensus

- Phase 2 (Weeks 5–8): Observability & Load Testing

  - Assign T26-style metrics and load harness to OpenAI

  - Your team: Metrics design, benchmark targets

  - OpenAI: Implementation, Prometheus integration, harness tooling

- Phase 3 (Weeks 9–14): Async Refactor

  - Critical: You define async boundaries (T85) before OpenAI codes

  - Assign T86a (consensus), T86b (network), T86c (storage) to OpenAI in parallel

  - Your team: Code review, integration testing, performance validation

9.2 Governance of Collaboration

Decision Points:

- [ ] Does OpenAI have production deployment authority? (No — recommend review gates)

- [ ] How are breaking changes handled? (Propose: change proposals must pass audit)

- [ ] Who owns final TestNet/MainNet decision? (Recommend: joint with external auditor)

- [ ] What's the escalation path for security findings? (Recommend: pause deployment, fix, re-audit)

Recommendation: Establish a steering committee (You + OpenAI + external security auditor) that gates major changes before TestNet/MainNet

Part 10: Audit Report Summary & Conclusion

10.1 Overall Assessment

| Dimension | Rating | Notes |
| --- | --- | --- |
| Cryptographic Design | A | Multi-suite framework sound; algorithm-agnostic; minor enforcement gaps (T82) |
| Consensus Logic | A | HotStuff correct; observability minimal; sync bottleneck will appear under load |
| Networking | B | KEMTLS ready; P2P infrastructure incomplete (peer discovery, backpressure) |
| Durability | D | Critical gap; must fix before TestNet |
| Performance | Unrated | No benchmarks; expected 500–1000 TPS with toy crypto; PQC impact unknown |
| Operational Readiness | C | DevNet feasible; TestNet risky without Phase 1; MainNet requires Phase 1–3 complete |

10.2 Go / No-Go Recommendations

| Environment | Current Status | Recommendation | Condition |
| --- | --- | --- | --- |
| DevNet | Ready | ✅ Proceed | Complete T82; run for 1 week stability test |
| TestNet Public | Not Ready | 🛑 Hold | Wait for Phase 1 (T82–T84) + Phase 2 (metrics/load) |
| MainNet | Not Ready | 🛑 Hold | Wait for Phase 1–3 complete + formal security audit |

10.3 Estimated Timeline to Production

Optimistic (All teams aligned, no blockers):

- Phase 1: 4.5 weeks → DevNet launch

- Phase 2: 5.5 weeks → TestNet public launch

- Phase 3: 7.5 weeks → MainNet ready (~ 17 weeks from now, late May 2026)

Realistic (Normal blockers, 30% schedule margin):

- Phase 1: 6 weeks

- Phase 2: 7 weeks

- Phase 3: 10 weeks

- Estimated MainNet: July 2026 (25 weeks from now)

Pessimistic (Major rework, performance surprises):

- Add 8–12 weeks for async refactor if bottleneck is worse than expected

- Add 4–6 weeks for governance key rotation protocol if design changes

- Estimated MainNet: September–October 2026 (40+ weeks from now)

10.4 Key Success Factors

- Complete Phase 1 on schedule — Persistence is blocking everything downstream

- Lock async design (T85) early — Prevents rework in T86

- Load test continuously — Discover bottlenecks incrementally; don't wait for TestNet

- Schedule formal security audit — Parallel to implementation; results inform fixes

- Communicate with validators & exchanges — Set expectations; avoid launch date surprises

References & Further Reading

Canonical Sources (From Project Logs)

- T0 conversation: Full project history, task breakdowns, design decisions

- T26: Network runtime observability proposal

- T70–T81: Cryptographic infrastructure completion

- T82–T85: Proposed future tasks (not yet started)

External Sources

- "A Scalable Post Quantum Secure Blockchain Framework with Adaptive Consensus" (Nature, 2025) — Post-quantum blockchain scaling insights

- NIST Post-Quantum Cryptography Standards (2022) — Algorithm agility design patterns

- HotStuff Consensus Paper (Moniz et al., 2020) — Safety and liveness invariants

- Devnet vs Testnet vs Mainnet (GatewayFM, 2024) — Deployment stage criteria

Appendix A: Crypto Suite ID Mapping (Reference)

Current (T81 Local):
├─ SUITETOYSHA3 = 0 (test-only SHA3 backend)
└─ Reserved for future PQ:
├─ SuiteID(1) = ML-DSA (planned)
├─ SuiteID(2) = SPHINCS+ (planned)
├─ SuiteID(3) = Falcon (optional)
└─ SuiteID(4–65535) = Reserved for future

Mapping Status:
├─ Wire format: Suite ID should be in all Vote/Proposal/QC messages (T81 added locally)
├─ Enforcement: Missing until T82 (startup validation)
├─ Rotation protocol: Defined at T82 time or later (T82+ spec)
└─ Backward compatibility: Not yet addressed (T82+ spec)

Appendix B: Checklist for Next Leadership Meeting

- [ ] Review Phase 1 timeline; confirm team capacity

- [ ] Approve Tokio async decision for T85; document assumptions

- [ ] Schedule formal security audit; select external firm

- [ ] Assign DevNet/TestNet infrastructure leads

- [ ] Confirm OpenAI collaboration scope & governance

- [ ] Set public communication (when will EEZO announce DevNet launch?)

- [ ] Review validator onboarding & key management procedures

- [ ] Discuss token economics & exchange integration timeline

End of Report

This audit reflects the project status as of January 15, 2026, based on 143+ conversations and 81+ development tasks (T0–T81). Recommendations assume continued OpenAI partnership and dedicated team engagement.